## Type of testing
Title |  | Type | Priority | Purpose | Tools | Planned for Release 1 | Comments
Backend unit tests | unit tests | Automation | 1 |  | pytest | Yes
Frontend unit tests | unit tests | Automation | 1 |  | testmagic | Yes
Functional Manual | Device testing | Manual | 1 | 1. To simulate the real world cases by using the actual devices like DTS, reader and mobile phones. 2. To cater maximum possible scenarios which will be performed by the actual users to minimize the risk of loosing data and to avoid system breakdown | DTS, reader, mobile phone | Yes
Functional Manual | API | Manual | 1 | 1. To test the bussiness logic as the business logic is written at API layer. | Postman | Yes
Functional Manual | UI | Manual | 1 |  | Browsers | Yes
TCP-API automation | API, TCP | Automation | 1 |  | J-Meter | Yes
Performance | TCP | Automation
Performance | API | Automation | 2 |  | Jmeter | Yes
Functional automation | API | Automation | 2 |  | NA | No | Lesser ROI
Performance | UI | Manual | 3 |  | NA | No | One API per page. As this is a SPA, so API perf is sufficient
Functional automation | UI | Automation | 3 |  | NA | No | Least ROI
Security | Tools | Automation | 4 |  | NA | No | Lesser ROI
Security | Manual | Manual | 5 |  | NA | No | Lesser ROI
Accessibility test | Manual | Manual | 5 |  | NA | No | B2B application, Users will be trained first.

## Testing road-map
Manual testing
Platform | Testing Type | Goals | Coverage Area | Owners | Tools/Resources | % coverage planned | Comment
* Web * Mobile app * IOT devices * Browsers -- Chrome(latest 2 versions) -- Firefox(latest 2 versions) -- Safari(latest 2 versions) -- Edge(latest 2 versions) -- IE(10 and 11) | Device testing | 1. To simulate the real world cases by using the actual devices like DTS, reader and mobile phones. 2. To cater maximum possible scenarios which will be performed by the actual users to minimize the risk of loosing data and to avoid system breakdown | 1. Testing user journey through mobile application. 2. Logging through DTS. 3. User journey through DTS and reader. 4. Testing differennt flows like: ---- login to DTS->enter site->enter room->start task->stop task->exit room-> exit site->log out from DTS ---- enter site(with mobile)->enter room->start task->stop task->exit room-> exit site(logout) | Neha Karan | DTS, Reader NFC tags Mobile phone | 100% | Needs to complete within the sprint
| API testing | 1. To test the bussiness logic as the business logic is written at API layer. | 1. APIs for entities CRUD. 2. APIs for reports generation. 3. APIs for barcode page, 4. APIs for download report and downloadd barcode feature. | Neha Karan | Postman | 100% | Needs to complete within the sprint
| UI testing | 1. To check the user experience. 2. To test if the product developed is functioning as expected. | 1. Testing of entities CRUD: employee, tasks, types, device commissioning etc. 2. Testing of reports: presence time, work time, statistics report. 3. Testing of barcode generation 4. Checking if the same data is reflecting in reports as sent by devices | Neha Karan | Browsers | 100% | Needs to complete within the sprint
| Regression | 1. To verify at hight level if all features of the product which are not part of automation scripts are working fine | 1. CRUD operations on few entities(mixed) 2. Testing if correct data is getting reflected in reports 3. Testing if user is able to download reports in all three formats 4. Verifying if barcodes are generated on webpage and reports
| Sanity | 1. Checking if all major features are working as expected before releasing new features to QA, UAT and prod environment, | 1. To check if all read only operation are working on entities. 2. To check if create and update is working on entities(except prod env.) 3. To check if reports are working 4. To check if user is able to download the reports. 5. To check if barcode is getting generated
| Smoke | 1. Checking if all major features are working as expected when we are deploying tickets on different servers | 1. To check if all read only operation are working on entities. 2. To check if create and update is working on entities(except prod env.) 3. To check if reports are working 4. To check if user is able to download the reports. 5. To check if barcode is getting generated
Automated testing | [8 empty] | Coverage planned
Platform | Testing Type | Goals | Coverage Area | Resources | Tools/Resources | % coverage planned | Frequency | Trigger | Sprint 55 | Sprint 56 | Sprint 57 | Sprint 58 | Sprint 59 | Sprint 60
* Web * Mobile app * IOT devices * Browsers -- Chrome(latest 2 versions) -- Firefox(latest 2 versions) -- Safari(latest 2 versions) -- Edge(latest 2 versions) -- IE(10 and 11) | Backend unit tests | 1. To write unit tests to test at method level so that most of the bugs are identified and fixed before it goes to QA. | 1. Methods written by devs | Sanjeev | pytest | 80% | * Can be multiple times in a day * When code is pushed to dev, qa and prod branch | When code is pushed to dev, qa and prod branch | 80% | 80% | 80% | 80% | 80% | 80%
| Frontend unit tests | 1. To write unit tests to test at method level so that most of the bugs are identified and fixed before it goes to QA. | 1. Methods written by devs | Kaushik | testmagic | 80% | * Can be multiple times in a day * When code is pushed to dev, qa and prod branch | When code is pushed to dev, qa and prod branch | 80% | 80% | 80% | 80% | 80% | 80%
| TCP-API automation | 1. TCP-API layer in SmartView has maximum business logic written which includes getting data from real devices and ingestions. 2. To simulate all major scenarios(after discussion with stakeholders) in automation script so that we detect any failure in these scenarios whenever we are deploying new code. | 1. Simulate the user journey device data(DTS/reader and mobile) and send it to TCP server. 2. Hit report APIs to check if correct data is reflecting | Neha Karan | JMeter | 50% | * Can be multiple times in a day When code is pushed to dev branch | * When code is pushed to dev branch. * Gitlab pipeline | 20% | 30% | 50% | 50% | 50% | 50%
| API Performance | 1. To check if our system is capable in responding within: < 5 seconds : for report APIs < 1 second for entities CRUD with 30 concurrent users | API response time and TPS | Neha Karan | JMeter | 100% | * Once in 3 sprints | manual | - | - | 100% | 100% | 100% | 100%
| TCP Performance | 1. To check if our system is capable in responding within: < 100 miliseconds : TCP data validation with 60 concurrent devices. | TCP response time | Karan | JMeter | 100% | * Once in 3 sprints | manual | - | 100% | 100% | 100% | 100% | 100%
| UI automation | 1. To test the CRUD operation is happening on entites with no user intervention. 2. To test if all the basic operation, table and columns are placed as expected on reports and barcode report page. | 1. Testing of entities CRUD: employee, tasks, types, device commissioning etc. 2. Testing of reports page: Just check columns and static page content 3. Testing of barcode generation: Just check columns and static page content | Neha Karan | Protractor | 50% to 60% | Daily | manual | - | - | - | 10% | 20% | 30%

## Releases
Release # | features
1 | * UI development of entities: employee, tasks, types, device commissioning etc. * UI development of reports: presence time, work time, statistics report. * UI development for barcode generation * Device data processing through the TCP server. * Ingesting TCP data into databases * Development of APIs for entities creation * Development of APIs for reports generation. * Development of APIs for barcode page, download report and barcode feature. * Email notification in-case data is not processed. * Integration with PAC APIs.

## Tech-stack
Objective | Tech Stack | Comments
Backend - APIs | Python
Device testing | DTS, reader, phone
UI functional | AngularJS
TCP server and data consumption(subscriber) testing | TCP, node.js | TCP - transport layer to get data from devices. The subscriber is to process the device data into DBs

## Performance testing
Information needs to be collected from client/analytics/stakeholders |  | We need to inform stakeholders before we run the performance tests if we are running these on QA/UAT server, because users will face system slowness during the execution.
Information | Action
What pages are going to get highest number(%age) of hits | Create script to simulate these number of hits on pages as every page is not expected to recieve saame number of hits
How much data will be present in the system after we go live | We need to create this much(Similar) data before we run our performance scripts
Concurrent user | Run script with these many concurrent users.
User types | what types of users are in the system and how many users of what type will be concurrent. Example: xyz.com might have 150 conmcurrent users, out of those 150 users: * 140 might be anonymous user * 2 admin users * 3 approver * 5 editor
Infrastucture | Infra of performance server must be in sync with production server
Think time | (UI performance) User takes some time to think/read when she opens a page and click on other link
logged in users | User logs in once and then repeat actions. So, use once only controller whereever applicable
Transaction per second | To simulate our scripts accordingly
Important points/component to be considered for script
Components | Comments
HTTP request default | Helps in changing the server details quickly without impacting any HTTP sampler.
HTTP Header manager | Keeps supplying headers to subsequent request within the same thread.
HTTP Cookies manager | Keeps supplying cookies to subsequent request within the same thread.
HTTP Caching manager | We need to enable this as by default, it is enables in browser.
Throughput controller | Used to divide traffic to pages in terms of percentage. Some pages might have higher traffic than others. Use multiple threshold controllers to cater different types of traffic on different pages
Uniform random timer | To simulate think time, use this timer.
Listners | Disable all listeners before running actual performance script. listener consumes extra resources of the system. Listeners can be used when we create a script
Assertions | Disable all assertions before running actual performance script. Assertion time adds up to the response time. Assertions can be used when we create a script List of asseertions that must not be used:

## Browsers
Browser | Version
Chrome | 65+ (Official Build)
Firefox | 54 +
Safari | 12+
IE | 10.x
IE | 11.x
Edge | 12+